## GUIDANCE
Risk Management
Risk management aims to minimise the impact of uncertainty on delivering project objectives. It is an ongoing process that involves:
• identifying and analysing potential risks
• developing strategies to manage risk
• monitoring and updating risk
• monitoring controls to ensure they are still in use and effective
• ensuring treatments are implemented
• when necessary, escalating risk to the attention of higher-level decision-makers or forums.
Effective risk management is about being open to an acceptable level of risk and actively managing that risk to achieve effective development outcomes.
DFAT development program risk management must consider fraud control; anti-corruption; countering terrorism resourcing (if relevant to the program); and environmental and other safeguards (including child protection; sexual exploitation, abuse and harassment (SEAH); and displacement and resettlement).
PRINCIPLES OF GOOD RISK MANAGEMENT
• Identify risks early: By identifying and addressing risk in the early stages of project planning and design, it may be possible to eliminate or greatly reduce risk through the design process.
• Proportionality: The approach to risk management must be proportionate to the level of risk and adaptable to suit changes in the environment. Eliminating risk is not the goal. Risk management involves considering ways to minimise risks, avoid risks, share risks or mitigate and accept risks. It is usually impossible and unrealistic to eliminate all risk in a development investment.
• Communicate, review, monitor and document: It is recommended that registers are reviewed and updated at least quarterly but may need updating more regularly depending on the nature of the risks, but at a minimum should be in alignment with the Annual Progress Report and Mid-Term Progress Report (if relevant). Ensure controls are still in place and that treatments have been implemented. Communicate and consult. Are risks being managed? By who? Do we have a common understanding of what the risks are? Are there new or emerging risks or is there information that may indicate that a risk event is occurring?
RISK DEFINITIONS
Risk: The effect of uncertainty on objectives.
Risk control: Measures in place to manage a risk.
Risk treatment: A process to modify or mitigate a risk.
Risk management: Identifying and analysing potential risks and opportunities, then developing proportionate, defensible management strategies that balance risk and treatment against benefits.
Risk escalation: Raising awareness of risk with higher forums or decision-makers
Risk and Safeguards Tool for DFAT's Partnerships for a Healthy Region Partners
Version: 27 September 2023
Risk and Safeguards Tool
This tool is intended to support DFAT partners who are engaged under the Indo-Pacific's Centre's Regional Health Partnersips in their risk assessment processes and risk management processes. It is acknowledged that it is only part of the risk management framework that partners should have in place to manage risk effectively.
To use the tool, Partners should work through the following steps:
1. Understand the category definitions and review the considerations for risk screening (tab 1)
2. Complete the risk register (tab 2) using the risk matrix (tab 3) to help you rate the level of likelihood and consequence. This requires you to a) Establish what success looks like before identifying the risk events; b) Identify risks; b) Evaluate risks; and c) Determine the risk velocity and risk response; and d) Treat the risk.
It is recommended that the risk register is reviewed quarterly to support effective risk management. At a minimum, Partners should review and submit risk registers with their 6 and 12 monthly reports and annual work plans.

## 1. CATEGORIES & RISK SCREENING
Please note: these categories and definitions are prompts for partners to consider, but are not necessarily an exhaustive list. Partners are not expected to answer or consider every question.
Category | Considerations
stakeholder | 1. Could a relationship breakdown occur with key partners or stakeholders, which would hinder the outcomes?
2. Does the intended implementing partner (and downstream partners) have the capacity and capability to fulfil their role?
3. Are there mechanisms (including in the design and agreement) in place to ensure there is adequate ongoing communication and reporting between consortia members and between DFAT and the implementing partner/s?
4. Do donors investing in health in the country/region have conflicting objectives?
5. Does the partner have sufficient ability to influence the stakeholder (e.g. multilateral organisations are harder to influence)?
6. Are there stakeholders who have negative attitude towards the program?
If in relation to a government, some risks may be better placed in the category of ‘Political’.
contextual | 1. Will increasing climate change impacts, including the extreme and slow onset of weather events, affect the intended outcomes of the program?
2. Is the program or intended outcomes exposed to natural hazards (disasters) that typically occur in the program area and/ or country?
3. Are there other external risk factors in the contextual (operational) environment that may impact on achieving the end of program outcomes?
resources | 1. Are there any significant weaknesses that mean public funds may not be used for intended purposes, not properly accounted for, or do not achieve value for money?
2. Are there any significant weaknesses that mean public funds may not be used in a way that is effective, efficient, economical and ethical?
3. Are there risks that could result in lost, stolen or misappropriated DFAT funds or assets?
4. Are there risks that could result in lost, stolen or damaged information or data that is deemed being official or sensitive information?
5. Does the activity involve multiple service (supply) chains where resource oversight may become difficult?
6. Will the partner be able to maintain sufficient levels of oversight of resources?
7. Are the implementing partner and downstream partners new to this kind of program?
8. Is there a history of fraud risk with the location, modality or implementing partners?
9. Will funds be front loaded, or paid through milestones?
10. Are there options to implement milestones and will milestones be verifiable?
11. Does the implementing partner or downstream partners have relevant ongoing or past fraud cases?
12. Have due diligence assessments highlighted fraud control issues?
13. Are there any external economic factors that may impact on achieving the end of program outcomes?
14. Are there any difficulties in terms of forecasting or securing the necessary budget to fulfil the end of program outcomes?
15. Is there the ability to manage service (supply) chain delivery, including any disruptions?
16. Does the partner have the ability to adequately influence the expenditure of public funds?
infrastructure | 1. Is the infrastructure that the program develops, or relies upon, at risk of damage from climate change impacts; for example, sea level rise or increased extreme weather events?
2. Could the infrastructure that the program develops or uses increase environmental or climatic vulnerability?
To evaluate climate change further, see the category of ‘Environmental’.
3. Could the program undermine environmental protection and biodiversity conservation partnerships?
4. Could the program impact on biodiversity conservation efforts, ecologically sustainable use of biodiversity, or exacerbating biodiversity loss (Chapter 5 of EPBC Act)?
5. Could the infrastructure design that the program develops or uses increase environmental or climatic vulnerability?
6. Is the infrastructure being designed and built in ways which fail to address constraints for women, people with disabilities and groups who experience social disadvantage and marginalisation to participate and benefit equally, as leaders, entrepreneurs, workers, and users of infrastructure?
Please note that this may be due to poor programming. If so, see the category of ‘Programming’.
7. Are there external infrastructure considerations, such as inadequate roads, electricity or health services that may affect end of program outcomes?
8. Are there technological considerations, such as IT infrastructure or changes, that may affect end of program outcomes?
political | 1. Does the partner government have the capacity and capability to perform its role in relation to the program?
2. Is there a possibility that political instability, or changes to a partner government’s strategy or policy, may affect the end of program outcomes?
3. Is there a likelihood for a change in government, which may impact on the end of program outcomes?
4. Might a change of government or existing political relations negatively affect a partner's relationship with the partner government?
5. Are there political sensitivities or controversies that may affect the partner's ability to sufficiently achieve end of program outcomes?
programming | 1. Is the program designed in ways which address underlying barriers and constraints for women, people with disabilities and groups who experience social disadvantage and marginalisation to participate and benefit equally? Is infrastructure designed and built to address constraints for women, people with disabilities and groups who experience social disadvantage and marginalisation to participate and benefit equally as leaders, entrepreneurs, workers, and users of infrastructure?
2. Will the program be able to address climate change and ecologically sustainable risks in building adaptive capacity and community resilience?
3. Is the program designed in a way that ensures it meets DFAT’s strategic objectives and addresses cross-cutting issues?
4. Are there any other programming risks that may impact upon the partner's ability to achieve end of program outcomes?
5. Are the end of program outcomes realistic and can they be achieved within the committed timeframe?
6. Are the outcomes sustainable?
7. Is there sufficient internal capacity and capability to achieve the end of program outcomes?
8. Are there adequate resources to implement the end of program outcomes?
9. Is there, or will there be, a business continuity plan in the event that risks are realised?
legal | 1. Is the program vulnerable to terrorism-resourcing, or non-compliance with relevant sanctions?
2. Will the program be implemented in or near terrorist-controlled territory?
3. Is there a risk that DFAT resources could be diverted for use by terrorists?
4. Is there a risk that the program could support a person or organisation on the DFAT Consolidated List or List of Terrorist Organisations?
Please determine if there are sanction requirements specific to the country where the program is implemented (see Sanctions regimes ¦ Australian Government Department of Foreign Affairs and Trade (dfat.gov.au).
5. Health and safety regulations (including asbestos management) breach
6. Could the program involve activities that adversely impact the health and safety of workers and/other persons?
7. Could the program involve locally engaged staff?
8. Could the program involve risk of exposing workers and/or communities to asbestos?
9. Could the program involve the demolition of a structure?
10. Could the program involve risk of exposing workers and/or communities to lead risk work?
11. Could the program involve risk of exposing workers and/or communities to prohibited carcinogens, restricted carcinogens, and restricted hazardous chemicals?
12. Could the program potentially breach partner country environmental laws or international environmental laws to which Australia and partner governments are a party?
13. Does the program address DFAT’s legislative obligations to control fraud?
14. Is there a possibility that in-country laws may be contravened?
15. Is there a possibility that international laws, or other international obligations, may be contravened?
16. Are there privacy considerations that need to be taken into account?
17. Are there any agreement, arrangement or contract management considerations?
environmental | 1. Will the program impact on biodiversity conservation efforts, ecologically sustainable use of biodiversity, or exacerbating biodiversity loss (Chapter 5 of EPBC Act)?
2. Will the program undermine environmental protection and biodiversity conservation partnerships?
3. Will the program involve the unsustainable use water, soil, vegetation and landscapes, limiting availability for future generations?
4. Will the program involve the generation of wastes, releasing of pollutants to air, water, and land including from poor waste management and disposal?
5. Will the program involve the manufacture, trade, and use of hazardous substances that are subject to international bans or phase-outs (such as ozone depleting substances)?
6. Will the program impact on natural and cultural heritage, including historical sites, landscapes and traditions and apply internationally recognised practices to manage potential impacts?
7. Will the program increase emissions of greenhouse gases (e.g. energy intensive process will lead to an increase in greenhouse gas production)?
8. Will the program reduce incentives to adapt to the impacts of climate change (e.g. change in social norms away from responsible water conservation to increased consumption, including for agriculture)?
9. Will the program increase the vulnerability of people? I.e. will agriculture/food security be impacted from the program (e.g. directly impacted such as removal of crops/land, and indirect impacts such as a reduction of key pollinating insects from increased use of introduced pesticides).
10. Will the program impact existing hardened infrastructure that may expose communities to sea level rise?
11. Will the program increase the potential impact of disaster (e.g. infrastructure building codes and specifications inadequate for the intensity of disasters/hazards experienced in the program area (e.g. floods, earthquakes, cyclones)?
12. Will the program lead to additional runoff into a marine environment? Will the program use water to supress dust or cut concrete, that may contribute to an increase in water runoff?
13. Will the program use hazardous chemicals and/or Petrol/Oil/Lubricants in the vicinity of a marine environment?
14. Will the program increase the community population and adversely affect local fishing practices or unsustainably harvest marine life?
social | 1. Could the program have an adverse impact on or create situations of harm for groups who experience social disadvantage and marginalisation including children, women, people with disabilities, Indigenous and ethnic minorities, older persons and other minority groups? (e.g. challenging power balance and control over resources which may predispose women, girls and people with disabilities to violence; activities which could reinforce negative attitudes and stigma towards disability; or poorly designed or lack of accessibility considerations into infrastructure, services and communications increasing risk of injury or illness).
2. Is there a risk that the program does not address gender inequalities generated by existing unequal norms, roles and relations? Beyond a compliance approach to ensure that women are not disadvantaged, programs must aim to meet both women’s and men’s distinct needs and design programs so that they help narrow gender gaps. This will entail taking specific action to address constraints for women to participate and benefit equally with men, as leaders, entrepreneurs, workers, et cetera.
3. Could the program risk leaving other groups who experience social disadvantage and marginalisation, including people with disabilities, further behind? (e.g. where targeted efforts have not been identified in the design to intentionally include people with disabilities, women's rights organisations and organisations of people with disabilities, or where there is no clear intention to track gender equality, disability equity and social inclusion). Has the program outlined how it will monitor for and avoid unintentional exclusion?
4. Have there been appropriate controls and treatments identified to manage potential risks and negative impacts for groups who experience social disadvantage and marginalisation, including women and people with disabilities? Does the program outline how it intends to monitor for unintended and negative impacts of the program using inclusive and accessible mechanisms?
5. Could the program involve contact with children or working with children?
6. Is there a risk of sexual exploitation abuse or harassment occurring in any aspect of the delivery of this activity (including activities implemented by downstream partners)
7. Does this activity include risk factors that exacerbate the sexual exploitation, abuse and harassment (SEAH) risks?
8. Could the program involve activities that adversely impact the dignity, human rights, livelihood systems or culture of indigenous people’s land or natural and cultural resources that Indigenous Peoples own, use, occupy or claim?
9. Could the program involve activities or provide advice about an activity that will: o displace people, either physically or economically; o exclude or reduce people’s access to land they live on or used to generate livelihoods; and/ or o exclude or reduce people’s access to land that is of cultural or traditional importance to them?

## 2. RISK REGISTER
Risk Register
<Enter name of program> | [9 empty] | What does success look like?
Inherent Risk Profile: | Please complete the Risk Register | Date of Last Review: |  |  |  |  | Next Review Date: |  |  | Establish what success looks like before identifying the risk events.
Residual Risk Profile: | Please complete the Risk Register | Program Manager: |  |  |  |  | Country/ies:
Category | Risk Event | Risk Sources | Risk Impacts | Risk Owner | Inherent Risk Rating |  |  | Existing Controls |  | Current (Residual) Risk Rating |  |  | Risk Velocity | Risk Response | Proposed Treatments | Treatment Owner | Treatments Implementation Date | Target Risk Rating |  |  | Does this risk need to be escalated?
| What could happen? | What could cause the event to happen? | What would happen if the event occurs? | Who is the person responsible for ensuring this risk is managed? | What is the level of risk before controls are applied? |  |  |  |  | What is the level of risk after controls are applied? |  |  | How quickly will the risk occur? | What is the appropriate response? | If no further treatment required or available, please explain why. | Person Responsible for Implementing Treatment/s |  | What is the level of risk anticipated once risk treatments have been applied? |  |  | Yes/No
[5 empty] | Likelihood | Consequence | Risk Rating | Controls | Control Effectiveness Effective/Partiaally effective/Ineffective | Likelihood | Consequence | Risk Rating | Fast (6months or less) Medium (9months or less) Slow (9 months or more) | Accept/Treat/Avoid |  |  |  | Likelihood | Consequence | Risk Rating
[5 empty] | Refer to matrix | Refer to matrix | Refer to matrix | What's currently in place? |  | Refer to matrix | Refer to matrix | Refer to matrix | [5 empty] | Refer to matrix | Refer to matrix | Refer to matrix
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -
|  | • | • |  |  |  | - | • |  |  |  | - |  |  | • |  |  |  |  | -

## 3. RISK MATRIX
CONSEQUENCES
|  |  | Limited | Minor | Moderate | Major | Severe
| Stakeholder | These risks are related to any stakeholders who are able to influence end of program outcomes, including any programs in connection with the investments. It can, for example, include implementing partners, beneficiaries, downstream partners, the public (Australian or otherwise),advocacy groups or any other stakeholder with the ability to impact on end of program outcomes. | The stakeholder has limited ability to influence the achievement of end of investment outcomes. The program is not reliant on this stakeholder to achieve end of investment outcomes. The stakeholder has a limited stake in the investment. | The stakeholder has minor ability to influence the achievement of end of the investment outcomes. The program is minimally reliant on this stakeholder to achieve end of investment outcomes. The stakeholder has a minor stake the investment | The stakeholder has moderate ability to influence the achievement of end of investment outcomes. The program is somewhat reliant on the stakeholder to achieve end of investment outcomes. The stakeholder has a moderate stake in the investment. | The stakeholder has major ability to influence the achievement of end of investment outcomes. The program is reliant on the stakeholder to achieve end of investment outcomes. The stakeholder has a major stake in the investment. | The stakeholder may have a severe (significant) ability to influence the achievement of end of investment outcomes. The program is fully reliant on the stakeholder to achieve end of investment outcomes. The stakeholder has a significant stake in the investment.
| Contextual | These are primarily external risks; that is, risks that exist in the operating environment but may negatively impact on the environment, such as natural hazards (disasters) or security concerns. It is often difficult to control the source, so controls and treatments seek to control the impact. | There are limited external contextual factors, and so, the external operating environment will have limited impact on the end of investment outcomes. | There are minor external contextual factors that may delay (3 months or less), but not prevent the achievement of end of investment outcomes. | There are moderate external contextual factors that may delay (6 months or less) but not prevent end of investment outcomes. The impact (e.g. damage to property) is fixable in the short-term. | There are major external contextual factors that may delay (9 months or less) and even prevent end of investment outcomes. The impact may temporarily reverse any results (e.g. damage to critical property or multiple properties). | There are severe (significant) external contextual factors that may delay (9 months or more), prevent or reverse end of investment outcomes. The event is likely to have a lasting impact and undermine sustainability (e.g. damage to critical infrastructure).
| Resources | These are risks primarily related to a partner's ability to manage its resources in alignment with PGPGA Act principles; for example, the ability to achieve value for money (VfM) or the administration of funds in a manner that is economical, ethical, efficient and effective. Resources also include considerations for the economy, such as inflation rates. | There are limited resource management vulnerabilities. The partner is able to maintain sufficient levels of oversight to monitor and control the appropriate use of public resources. | There are minor resource management vulnerabilities. The partner can mostly monitor the appropriate use of public resources. | There are moderate resource management vulnerabilities. The partner has some ability to monitor and control the appropriate use of public resources. | There are major resource management vulnerabilities. The partner has minimal ability to monitor and control the appropriate use of public funds. | There are severe (significant) resource management vulnerabilities. The partner inability to monitor and control public resources may mean it undermines the overall financial viability of the investment.
| Infrastructure | These are risks primarily related to technological infrastructure or infrastructure that is essential to the community (such as roads or health services). It also includes infrastructure that is necessary to fulfil the end of investment outcomes and maintain sustainability. | There are limited infrastructure inadequacies, but there are ways to work around them to achieve end of investment outcomes. | There are minor infrastructure inadequacies may cause delay (3 months or less) and hinder the ability to achieve end of investment outcomes. | There are moderate infrastructure inadequacies may cause delay (6 months or less) or reduce the effectiveness of end of investment outcomes. | There are major infrastructure inadequacies may cause delay (9 months or less) or negatively impact on the sustainability of the investment. | There are severe (significant) infrastructure inadequacies may cause delay (9 months or more) and/ or negatively impact on the sustainability of the investment.
| Political | These are risks that primarily relate to risks that stem from an offshore government’s actions, and the extent to which these actions may hinder DFAT’s ability to achieve end of investment outcomes. It also includes any risks which may impact on DFAT’s ability to plan or support the Australian Government, as well as influence the Australian Government or offshore governments. | There are limited political factors that may threaten the investment and these factors can be easily managed. | There are minor political factors may cause delay (3 months or less) and hinder the ability to achieve end of investment outcomes. The partner or DFAT) is well-positioned to influence these factors. | There are moderate political factors that may cause delay (6 months or less) or reduce the effectiveness of end of investment outcomes. The partner (or DFAT) can influence these factors with significant effort. | There are major political factors may cause delay (9 months or less) or negatively impact on the sustainability of the investment. | There are severe (significant) political factors that may cause delay (9 months or more) and/ or negatively impact on many investments, and/ or the entire country program.
| Programming | These are risks that relate to the technical aspects of the program design. This extends to, for example, risks stemming from the program rationale, analytical underpinnings, technical soundness and complexity, or design flexibility that could hinder departmental ability to achieve end of investment outcomes. These are primarily internal risks that stem from the ability to design a program in a way that achieves the intended results. | There are limited programming inadequacies, and these inadequacies can be dealt with by routine operations. | There are minor programming inadequacies, which may cause delays (3 months or less) to achieving end of program outcomes. | There are moderate programming inadequacies, which may cause delays (6 months or less) to achieving end of program outcomes. | There are major programming inadequacies. which may cause delays (9 months or less) or prevent the achievement of one (1) or more end of program outcomes. | There are severe (significant) programming inadequacies. which may cause delays (9 months or more), and/ or are likely to prevent the achievement of the end of program outcomes.
| Legal | These are risks that primarily relate to contractual compliance, and legislative compliance. For contraventions of Australian or other laws, assume a ‘major’ or ‘severe’ impact, given DFAT is not in a position to contravene legal or regulatory obligations. Place greater reliance on the ‘probability’ table below to make this assessment. If needed, seek legal advice to ensure investments are implemented in a lawful manner. | If a funding recipient is involved, the event may cause a limited contravention of agreement or arrangement terms. In this event, no agreement or arrangement management (contract management) is required. For contraventions of Australian or other laws, assume a ‘major’ or ‘severe’ impact. Place greater reliance on the ‘probability’ table below to make this assessment. | If a funding recipient is involved, the event may cause a minor contravention of agreement or arrangement terms. In this event, only verbal discussion to facilitate their compliance is required. For contraventions of Australian or other laws, assume a ‘major’ or ‘severe’ impact. Place greater reliance on the ‘probability’ table below to make this assessment. | If a funding recipient is involved, the event may cause a moderate contravention of agreement or arrangement terms. In this event, the funding recipient would receive a formal letter and ongoing contract/ performance management to support compliance. For contraventions of Australian or other laws, assume a ‘major’ or ‘severe’ impact. Place greater reliance on the ‘probability’ table below to make this assessment. | If a funding recipient is involved, the event may cause a major contravention of agreement or arrangement terms. In this event, the funding recipient would receive a formal letter of suspension or termination until they are able to restore compliance. For contraventions of Australian or other laws, assume a ‘major’ or ‘severe’ impact. Place greater reliance on the ‘probability’ table below to make this assessment. | If a funding recipient is involved, the event may cause a, or several, severe (significant) contravention of agreement or arrangement terms. In this event, the funding recipient would have their agreement or arrangement terminated as the default. For contraventions of Australian or other laws, assume a ‘major’ or ‘severe’ impact. Place greater reliance on the ‘probability’ table below to make this assessment.
| Environmental | These are risks that primarily relate to risks that, when in pursuit of end of program outcomes, action may negatively impact on the environment. It may also include risks that impact on DFAT’s ability to improve environmental outcomes. Please note that natural hazards (disasters) is captured by the category of ‘contextual’. These risks should consider the nature, scale and significance of direct and indirect environmental impacts. | Limited impact on the environment. Impacts are largely undetectable. No or negligible increase to climate change impacts, and/ or negligible GHG emissions. | Minor impact on the environment. Impacts are temporary and confined to a small area of low environmental sensitivity. Minimal and short-term increase to climate change impacts, and/or minimal GHG emissions. | Moderate impact on the environment. Impacts may be long lasting, extend beyond the local area and include sensitive environmental communities. Moderate and short-term increase to climate change impacts, and/or moderate GHG emissions. | Major impact on the environment. Impacts are irreversible, diverse, over a sensitive geographic area. Significant and long-term increase to climate change impacts, and/or significant GHG emissions. | Severe (significant) impact on the environment. Impacts are irreversible, diverse, with strong cumulative impacts over a large and/or sensitive geographic area. Severe and permanent increase to climate change impacts, and/ or very high GHG emissions.
| Social | These are risks that primarily relate any risks that, when in pursuit of end of program outcomes, departmental action may negatively impact on people. For example, gender identity, children, persons in vulnerable situation or who experience social disadvantage as well as resettlement and displacement of persons. These risks should define the nature, scale and significance of direct and indirect social impacts. | For this category, assume a ‘major’ or ‘severe’ impact, if it is difficult to determine harm to a person. Place greater reliance on the ‘likelihood’ axis to make this assessment.
|  | PROBABILITY | CONSEQUENCES
LIKELIHOOD | Almost Certain | The event is expected to occur regularly under normal circumstances. More than 80% chance of occuring | Medium | Medium | High | Very High | Very High
| Likely | The event is expected to occur at some time. 60-80% chance of occurring | Medium | Medium | High | High | Very High
| Possible | The event may occur at some time. 40-60% chance of occurring. | Low | Medium | Medium | High | High
| Unlikely | The event may, but is not likely to, occur in normal circumstances. 20-40% chance of occurring | Low | Low | Medium | Medium | High
| Rare | The event may occur in exceptional circumstances but has not occurred yet. Less than 20% chance of occurring | Low | Low | Low | Medium | Medium